## Sheet1
PRODUCT BACKLOG
ID | ITEM | OWNER | SPRINT NO: | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | Team Member | NOTES
USER LOGIN AND CREATING AND ACCOUNT
2 | As a customer I want to link my email so that I can login easier and faster. |  | 1 | High | 1 | IN PROGRESS | Passes all acceptance and unit tests, Code is merged to the developer branch, Email field is present on user form, input data is checked serverside against an email regular expression, data is saved in the Customer table in the database | Ghaida
3 | As a customer I want to link my phone number to my account so that the company can get in contact with me. |  | 1 | High | 1 | IN PROGRESS | Passes all the unit and acceptance test, phone number is present in the database, when edited in the user profile, it is updated in the database, wrong format numbers are rejected. code is merged to the developer branch | Jack
4 | As a customer I want to link my address so that the company can send me my billing statements. |  | 1 | High | 1 | IN PROGRESS | Ghaida | Jack
5 | As a customer I want to link my name to my account so the company knows who I am. |  | 1 | High | 1 | IN PROGRESS | Passes all Acceptance and unit tests, code is merged to the developer branch, first and last name fields exists on the create account form, regex exists, corresponding fields exist in customer database, no bugs are present when users attempt to use this feature, Trello board updated | Dulshan
6 | As a user I want a password linked to my account so that it is secure. |  | 1 | High | 2 | IN PROGRESS | Passes all Acceptance And unit tests, code is merged to the developer branch, project builds without error, Product backlog is up to date, Bugs in program have been fixed, trello board has been updated, coding conventions have been met, Password has passed regex and encrypted succesfully, Assumptions of user stories have been met | Dulshan
13 | As a customer I would like to be able to create an account so that I am able to make a booking. |  | 1 | High | 3 | IN PROGRESS | Passes all acceptance and unit tests, Code is merged to developer branch, account creation page exists in the web app, Customer table exists in the database, form contains all fields relevant to the user account and upon submission of the user form the inputs are validated and details are saved to the customer table. | Julian
14 | As a customer I would like to be able to log in to my account so that I can make a booking. |  | 1 | High | 1 | IN PROGRESS | Passes all the unit and acceptance tests, the login form accepts only the email and the password, the wrong formats are rejected, password section is blurred when typing, the data is processed on the server side, password is hashed and compared to the hash value in the database and if the password and the username are the same, the user is taken to the profile. | Julian
CHANGING/VIEWING ACCOUNT DEATAILS
8 | As a customer, I want to see all my active bookings, so that I can change them if required. |  | 3 | High | 3 | PENDING | Ghaida | Julian
9 | As a customer, I want to see my current profile so that I can check if my details are correct. |  | 3 | Low | 3 | PENDING | Passes all Acceptance and unit tests, code is merged to the developer branch, profile page exists in application, all data attached to the logged in account (excluding password) is displayed on the page, no bugs are present when users attempt to access this page, trello board updated. | Theo
10 | As a customer, i want to edit my phone number so that my details are kept up to date |  | 3 | High | 3 | PENDING | Phone number passes regular expresion succesfully, acceptance and unit tests Have been completed succesfully, project builds without errors, phone number stores in database succesfully, codding conventions/standars have been meet, product backlog is up to date, trello board has been updated, Assumptions of the user stories have been met. bugs have been fixed, code has been pushed to the developer branch, meets product owners expectations | Theo
11 | As a customer, i want to edit my name so that i can keep it up to date if i get my name changed |  | 3 | High | 2 | PENDING | Passes all Unit and Acceptance tests, meets Development team and Product owners expectations, Code has been merged to the developer branch. Name Field is present in the Customer table in the database, an edit account form is present on the front end, | Theo
12 | As a customer i want edit my email address so that i can keep it up to date |  | 3 | High | 3 | PENDING |  | Theo
17 | As a customer I would like to change my account password so that I can keep my account secure. |  | 3 | High | 2 | PENDING |  | Jack
27 | As an owner, I want to see clients contact details, so I can contact them if circumstances change |  | 3 | Low | 1 | PENDING |  | Ghaida
MAKING A BOOKING AND VIEWING BOOKINGS
7 | As an owner, I want to be able to see all previous bookings, so that I can maintain a record |  | 2 | Low | 3 | PENDING |  | Julian
15 | As a customer I would like to see the service I am booking so that I know it is the right service. |  | 2 | High | 4 | PENDING |  | Ghaida
16 | As a Customer I would like to see the staff member conducting my service so that I can make a booking with my preferred staff member. |  | 2 | Moderate | 4 | PENDING |  | Ghaida
18 | As a customer I would like to cancel a booking so that I can change my schedule. |  | 2 | High | 1 | PENDING |  | Theo
23 | As customer I want to book a service so that i dont have to call the service up. |  | 2 | High | 2 | PENDING |  | Jack
24 | As a customer I want a list of my previous bookings so that I can easily re-book the same services. |  | 2 | Low | 2 | PENDING |  | Jack
26 | As an owner, I want to remove bookings, so that I can manage bookings when unusual circumstances arise. |  | 2 | Moderate | 2 | PENDING |  | Dulshan
28 | As a Customer, I want my details to be recorded, so I can create bookings quickly. |  | 2 | High | 1 | PENDING |  | Ghaida
29 | As a Customer, I want to view what bookings are available, so I can book an appropriate time |  | 2 | High | 5 | PENDING |  | Julian
32 | As an Administrator I want to view all new bookings so that I can plan and organize the new roster. |  | 2 | Low | 3 | PENDING |  | Dulshan
1 | As the owner I want to see all the bookings done for each person so that I can see how busy we are for that day/week. |  | 2 | Low | 4 | PENDING | Passes all Unit and Acceptance tests, meets Development team and Product owners expectations, Code has been merged to the developer branch. | Dulshan
EMPLOYEE/BUSINESS MANAGEMENT FEATURES
21 | As a worker I would like to edit my availability so that I have the flexibility to change my schedule if something unexpected where to occur. |  | 4 | Low | 7 | PENDING |  | Julian
22 | As a business provider I want to add my business trading hours so that customers don’t book outside active trading hours. |  | 4 | High | 3 | PENDING |  | Theo
19 | As a worker I would like access to my profile so that I can see my assigned working hours. |  | 4 | High | 3 | PENDING |  | Ghaida
20 | As a worker I would like to see the service that I will be providing so that I can prepare for my shift. |  | 4 | Moderate | 4 | PENDING |  | Ghaida
25 | As an owner, I want to be able to accept or decline a request to book so that I can manage my services properly. |  | 4 | Low | 4 | PENDING |  | Jack
30 | As an Administrator I want to be able to edit employee information so that employee information is kept up to date. |  | 4 | Moderate | 3 | PENDING |  | Dulshan
31 | As an Administrator, I want to be able to see employee availability so that I can create a new working roster |  | 4 | Low | 4 | PENDING |  | Dulshan