## Sheet1
SPRINT BACKLOG
PBI ID | PBI ITEM | TASK ID | TASK | ASSIGNED TO | STATUS
14 | As a customer I would like to be able to log in to my account so that I can make a booking. | 14.1 | Create a login page(Be able to login with email and password) | Julian Rizzo | In porgress
|  | 14.2 | Create the database and populate it with the Customer table | Jack Williams | In porgress
|  | 14.3 | Create the static home screen | Julian Rizzo | In porgress
|  | 14.4 | Validate all user input from login page | Theo Politis | In porgress
|  | 14.5 | Authenticate user input with information in the database | Theo Poltis | In porgress
|  | 14.6 | Perform unit tests and acceptance tests | ghaida alharbi | In porgress
2 | As a customer i would like to link my email to my account so that i can login faster | 2.1 | Use Regular expression to validate the email format | Jack Williams | In porgress
|  | 2.2 | Be able to store the email information into the database | Jack Williams | In porgress
|  | 2.3 | Perform unit tests and acceptance tests | Jack Williams | In porgress
3 | As a Customer i would like to link my phone number to my account so the company can get in contact with me | 3.1 | Use regular expressions to validate the format of the number | Theo Politis | In porgress
|  | 3.2 | Phone number should pass annotations in customer model | Theo Politis | In porgress
|  | 3.3 | Validated phone number should be stored in the database | Theo Politis | In porgress
|  | 3.4 | Perform unit tests and acceptance tests | Theo Politis | In porgress
4 | As a customer i would like to link my address so that the company can send me billing statements | 4.1 | Validate the address in the front end using regular expressions | ghaida alharbi | In porgress
|  | 4.2 | Be able to store the address data in the database | ghaida alharbi | In porgress
|  | 4.3 | Perform unit tests and acceptance tests | ghaida alharbi | In porgress
5 | As a Customer i would like to link my name to my account so that the company knows who i am | 5.1 | Validate First name and last name input with regular expressions | Dulshan Kodithuwakku | In porgress
|  | 5.2 | Be able to store the first name and last name in seperate fields in the database | Dulshan Kodithuwakku | In porgress
|  | 5.3 | Use Annotations to check the input before storing in database | Dulshan Kodithuwakku | In porgress
|  | 5.4 | Perform unit tests and acceptance tests | Dulshan Kodithuwakku | In porgress
6 | As a user i want a password link to my profile so i can login securly | 6.1 | Password must pass a Regex | Theo Politis | In porgress
|  | 6.2 | Encrypt pass word before entering into the databse | Theo Politis | In porgress
|  | 6.3 | Setup encryption key | Theo Politis | In porgress
|  | 6.4 | Use Annotations to check the input before storing in database | Theo Politis | In porgress
|  | 6.5 | Store encrypyed key into the database | Theo Politis | In porgress
|  | 6.6 | Perform unit tests and acceptance tests | Theo Politis | In porgress
13 | As a user i want to create an account so that i able to make a new booking | 13.1 | devolop a create an account page(First name, Last Name, mobile, address, email, password, username | Julian Rizzo | In porgress
|  | 13.2 | Be able to sumbit the information in the front end to the backend | Julian Rizzo | In porgress
|  | 13.3 | perform acceptance tests on front end page | Julian Rizzo | In porgress